## Project Calendar
Milestone | Dates | Week | Task | Details | Deliverables
M1: Foundations locked | Sat 8 – Fri 14 Aug | 1–2 | Literature review + user journey map | Read up on Pandapower digital twins, hosting capacity estimation, HIL testbeds, and ML surrogate models for grid state. In parallel, sketch the operator's user journey: voltage alert -> hosting capacity estimate -> curtailment decision -> dashboard view. This journey map is now a required deliverable, not just background reading. | Lit review notes, user journey map, architecture finalized, demo-screen decision made
|  |  | Lock architecture and decide your demo screen | Finalize the data flow: 5 ESP32 nodes -> Raspberry Pi -> Pandapower digital twin -> ML model -> hosting capacity output -> Embedded Node + dashboard. Decide now what your 'screen' will be (own minimal UI vs. feeding Somachandra's Grafana/Node-RED dashboard) so you're not scrambling before the demo.
M2: Digital twin operational | Sat 15 – Fri 21 Aug | 3 | Build the Pandapower digital twin | Install Pandapower and model a radial feeder with a transformer and 5 household buses, matching a standard IEEE low-voltage test feeder. Confirm basic power flow calculations run correctly. | Working Pandapower feeder model, validated power flow
M3: Training data + model | Sat 22 – Thu 27 Aug | 4–5 | Generate synthetic training data | Run the digital twin across varied load/PV/time-of-day scenarios, recording resulting grid state plus true maximum safe hosting capacity per scenario, to build your ML training set. | Synthetic dataset generated, RF/XGBoost trained and compared, model frozen
|  |  | Train and evaluate the ML model | Train Random Forest and XGBoost on the synthetic data, compare accuracy against true power flow results and inference time (<10ms target). Pick the better model and freeze it for the demo.
M4: Raspberry Pi + single-node test | Fri 28 – Sun 30 Aug | 6 | Set up the Raspberry Pi environment | Install Python, Pandapower, your ML libraries, and an MQTT client on the Pi. Get it talking to at least one ESP32 node before scaling to all 5. | Pi environment running, one ESP32 talking to it successfully
M5: Full HIL + demo screen | Mon 31 Aug – Wed 2 Sept | 7–8 | Wire up the full HIL loop | Connect all 5 physical ESP32 nodes so live sensor readings plus the digital twin's simulated transformer data both reach your trained model. This is the 'core workflow' you'll actually run live on presentation day. | All 5 ESP32 nodes integrated, live output visible on your screen/dashboard panel
|  |  | Build your demo screen | Build the minimal screen/output you decided on in step 2 - a live-updating value, small web page, or dashboard panel - so there's something visible to point to, not just numbers in a terminal.
M6: Feedback + rehearsal | Thu 3 Sept (buffer, tight) | 9–10 | Supervisor/power-engineer walkthrough | Run the walkthrough with supervisor/power-engineer, capture feedback, rehearse the live demo, and prepare a fallback recording in case of technical issues. | Supervisor/power-engineer walkthrough done, feedback captured, live demo rehearsed with a fallback recording ready
Proposal Presentation | 3–7 Sept | — | Proposal Presentation | Deliver the live demo covering the user journey, the working core workflow, the system architecture, and evidence of feedback incorporated. | Live demo: user journey, working core workflow, architecture, feedback evidence
Write-up phase | 8–14 Sept | — | Write-up phase | Turn the presentation demo and results into the Proposal Report, aligned with the other 3 team members' sections. | Draft Proposal Report sections
Proposal Report Submission | 15 Sept | — | Proposal Report Submission | Finalize and submit the complete Proposal Report. | Final document